# Automation & Operational Technology

# OT Automation Machine – Work Package

### Document Control

| Version No. for Final Release | 1.0 |
| --- | --- |
| Issue Date | 01-01-2026 |
| Status: Draft or Final | Draft |
| Document Owner | UID |
| Audience | XXXXX |
| Approval for Final Release | Draft |

### Project Overview / Warehouse Details

Project Name:

FBM ID:

Site address:

SITE ID:

Dates:

MS1.1 – Provision of Supplier - xx/xx/2026

MS1.2 – Provision of Design - xx/xx/2026

MS2 – Factory Acceptance / Lab Testing / Simulation - xx/xx/2026

MS3 – Unit Testing - xx/xx/2026

MS4.1 – Site Integration - xx/xx/2026

MS4.2 – UAT (User Acceptance Testing) - xx/xx/2026

MS5 – Hypercare - xx/xx/2026

MS6 – Business as Usual Support - xx/xx/2026

# 1. OT Machine – Scope Overview

This document defines the scope of work for design, supply, installation, integration, commissioning, and handover of Operational Technology (OT) machines within the warehouse.

### Covered OT Equipment (non-exhaustive)

- Cubic and Weighing-Dimensioning Units

- RFID Tunnels

- RFID Portals

- PANDA / Automated Print & Apply Systems

- Carton Erecting Machines

- Carton Closing / Sealing Machines

- Labelling & Scanning Stations

- Future OT expansions as per site roadmap

# 2. Functional Requirements

- OT machines must support target throughput and accuracy KPIs defined by Operations. – Appendix X

- OT machines shall ensure high accuracy for weight, dimension, RFID, and barcode data.

- Equipment must integrate seamlessly with:

  - Conveyor systems

  - Warehouse Control System (WCS/MCS)

  - Warehouse Management System version (WMS)

- Machines must support 24/7 operations unless otherwise specified.

- Equipment must allow safe manual override and maintenance access.

- All OT machines must comply with local safety, electrical, and industrial standards.

- Machines must support data capture and transmission for operational analytics.

- OT machines shall detect, classify, and report operational faults and process exceptions.

- OT machines shall provide clear and understandable fault and alarm messages to operators.

- OT machines shall comply with internal AOT standards, customer requirements, and regulatory obligations. Appendix X

# 3. Technical Requirements

### 3.1 Mechanical Requirements

- Product dimensions & weight range

- Maximum throughput capacity (cartons/hour) under continuous operation

- Duty cycle

- Machines must be mechanically compatible with:

  - Conveyor height (if applicable)

  - Conveyor width (if applicable)

- Structural frame type.

### 3.2 Electrical Requirements

- Power Supply:

  - Voltage: [230V / 400V]

  - Frequency: [50Hz]

  - Phase: [Single / Three Phase]

  - Rated power consumption (kW)

- Proper grounding and bonding mandatory for all equipment.

### 3.3 Control System & PLC Requirements

- PLC make and model

- PLC control architecture [Components].

- Standardized I/O mapping and signal naming.

- PLC Integrated Portal License

- Support for:

  - Start / Stop

  - Fault / Alarm

  - Status feedback

- Remote diagnostics capability. (if required - SCADA)

### 3.4 Network & IT/OT Integration

- Supported industrial communication protocols and versions

- Industrial Internet connectivity

- Network bandwidth requirements per machine

- Unique asset ID for each OT machine.

- IP addressing and VLAN allocation as per IT standards.

- Wireless connectivity support (if applicable) using Siemens iPCF or Cisco URWB for industrial mobility and roaming

- Support for industrial communication protocols including OPC-UA, MQTT, Profinet, Modbus TCP, and REST API for system integration

### 3.5 RFID Systems (if applicable)

- RFID frequency band as per regional regulations.

- Tag Compatibility as per regional regulations.

- Tunnel and portal read accuracy %

- Cargo Profile Type (Box of WHAT item)

- Middleware integration with WCS/WMS.

- Read event logging with timestamp and location.

- Diagnostic tools for antenna and reader health

- Shielding to prevent cross-reads.

### 3.6 Cubic / Dimensioning Systems (if applicable)

- Supported carton size range

- Supported package shapes (regular, irregular, soft packs)

- Weight accuracy

- Dimension accuracy

- Automatic calibration and verification routines.

- Data transmission in real time to WMS/WCS.

### 3.7 PANDA / Print & Apply Systems (if applicable)

- Label formats supported: [GS1 / Customer-specific]

- Print resolution: [300 dpi minimum]

- Apply accuracy

- Integration with label data source (WMS/WCS)

- Supported barcode symbologies (Code128, QR, GS1-128, etc.)

### 3.8 HMI & Operator Interface (if applicable)

- Industrial HMI panels with:

  - Machine status

  - Alarm diagnostics

  - Manual controls

- HMI screen response time and refresh rate

- Role-based access (Operator / Maintenance / Admin).

- Alarm history and event logs.

### 3.9 Safety Requirements

- Compliance with:

  - ISO 12100 (Risk Assessment)

  - ISO 13849 (Funcational Safety)

  - ISA/IEC 62443 (Cybersecurity)

  - Local machine safety regulations

- Clearly marked E-Stops.

- Light curtains / safety scanners where required.

- Lockout-Tagout (LOTO) provisions.

- Safety signage and operator instructions.

### 3.10 Data Logging & Diagnostics Requirements

- Logging of operational events and faults.

- Timestamped alarm and event records.

- Retention of logs across restarts.

- Diagnostic information for troubleshooting.

### 3.11 Server Details

- Number of Centralized servers for OT data processing, storage, and integration with MCS/WMS.

- Server sizing based on operational load and future scalability requirements.

- Server hardware details (CPU / RAM / Storage).

- Virtualized server environment for OT applications.

- Server specification should be mentioned in Minimum and Optimal server requirements.

- High availability and fallback to prevent data loss.

- Approved server vendors (e.g., Nutanix, OnLogic, or equivalent).

## 4. Deliverables

Planning

MS1.1 – Provision of Supplier – delivery date

- Full Bill of Materials (BoM) submitted and validated, including manufacturer, model, part numbers, port/component specifications, and compliance certifications

- Approved Purchase Orders confirmed for all equipment and professional services

MS1.2 – Provision of Design - delivery date

- Design documentation issued: network topology, connectivity diagrams, rack elevation diagrams, floor plan layouts, IP schema, VLAN and segmentation design, and cable routing plans

- Procurement and delivery of all equipment as defined in Sections 1–3 initiated and tracked against BoM

Execute

MS2 – Factory Acceptance / Lab Testing / Simulation - delivery date

- Full BoM receipt confirmed; manufacturer warranty coverage verified for all equipment and components

- Pre-staging and configuration completed as per Section 3 technical requirements

- Factory acceptance testing executed and signed off prior to site delivery

MS3 – Unit Testing - delivery date

- Physical installation and commissioning of all equipment on site, including accessories, peripherals, mounting hardware, and cabling

- As-built drawings and installation photos produced, reflecting final installed routes, placements, termination points, and labelling

- Certified test reports produced for all applicable runs and systems (e.g. Fluke cable certification, UPS runtime, RF coverage, VLAN and uplink validation)

- Compliance documentation confirmed against applicable standards (ANSI/TIA-568, ISO/IEC 11801, fire safety, and any OT-specific industrial standards)

MS4.1 – Site Integration - delivery date

- Connectivity and integration testing completed across network, power, and application layers

- Validation evidence confirms all delivered equipment meets Section 3 requirements; outstanding items logged in a punch list with agreed resolution dates

MS4.2 – UAT (User Acceptance Testing) - delivery date

- Operations UAT completed and signed off by site management

- Asset inventory compiled: device type, model, serial number, firmware version, and registered in snow CMDB

- Devices mapped to assigned users, workstations, rooms, or operational areas

- RF Guns/RDT devices registered in SOTI as a mandatory task

- All documentation delivered in soft copy formats

- Formal handover of equipment to site management, including credentials and escalation contacts

Go Live

MS5 – Hypercare - delivery date

- Hypercare support active during agreed initial operational period; incidents logged and resolved

- NOC monitoring confirmed active and initial SLA report issued (where applicable)

- All handover documentation validated as complete: as-built drawings, configuration backups, test reports, compliance records, asset register, and warranty certificates

MS6 – Business as Usual Support - delivery date

- Final project acceptance signed off; project formally closed

- Support transitioned to BAU team with full handover pack, escalation matrix, and SLA documentation in place

- All outstanding punch list items resolved or formally accepted and transitioned to BAU tracking

Appendix 1 – Site Layout

Attach Site layout diagram.

# Appendix 2 – AP Locations & Heatmap

Attach Network Heatmap.

# Appendix 3 – Rack Elevation Diagram

Attach Rack elevation diagrams.

# Appendix 4 – Network Topology

Attach Network topology diagram.

# Appendix 5 – Concept Design

Attach Concept Design.

# Appendix 6 – Value Stream Mapping

Attach VSM.